## Overall Progress sheet
Progress Sheet (Physical & Financial)- PEACE-II (Updated on 18th Nov 2025)
S. No | Activity | Unit | Project Targets | Progress | Remaining | Total Cost | Expenditure | Balance
A | Output 1.1 – Community-Based Micro & Mini hydropower plants
1 | Technical surveys, designs and cost estimates | MW | 16.3 | 12.7 | 3.6 | 0 | 0 | 0
2 | Construction/rehabilitation of community-based HPPs (16.3 MW). | MW | 16.3 | 2.5 | 13.8 | 6532368421.0526 | 1490000 | 6530878421.0526
3 | Participatory workshops/dialogues/broad-based meetings and exposure visits (governance and management of HPPs) | Dialogues | 16 | 6 | 10 | 10600000 | 0 | 10600000
4 | Sessions on safe use of electrical appliances for women groups | Individuals | 3000 | 0 | 3000 | 6450000 | 0 | 6450000
5 | Training MHP's staff (managing and maintaining the HPPs) | Individuals | 500 | 0 | 500 | 3387500 | 0 | 3387500
6 | Micro-Grid | Assessment | 1 | 1 | 0 | 2642543.8596 | 0 | 2642543.8596
7 | Establishment of a Micro Hydro Network at the provincial level for policy advocacy and knowledge sharing on renewable energy | Network | 1 | 0 | 1 | 6480000 | 0 | 6480000
8 | Establishment of Energy Company | Company | 1 | 0 | 1 | 28539473.6842 | 218500 | 28320973.6842
B | Output 1.2 – Community-Based Irrigation Systems communities
1 | Construction/rehabilitation of Irrigation System (Climate resiliant) | Schemes | 100 | 12 | 88 | 1014736842.1053 | 0 | 1014736842.1053
2 | Capacity building of community on O&M | Dialogues | 100 | 12 | 88 | 7950000 | 0 | 7950000
C | Output 1.3 - Community-Level Sustainable Natural Resources Management
1 | NRM plans, DRR dimension | Plans | 100 | 0 | 100 | 5300000 | 0 | 5300000
2 | Slope stablization/afforestation/land protection (150 hectares) | Schemes | 100 | 0 | 100 | 528508771.9298 | 0 | 528508771.9298
D | Output 2.1 - Economic Growth- Existing small local business are strengthened
1 | Participatory Survey | Assessment | 1 | 0 | 0 | 5285087.7193 | 0 | 5285087.7193
2 | Capacity Building | SMEs | 600 | 0 | 600 | 122085526.3158 | 0 | 122085526.3158
3 | Cost-sharing grants (in cash/in-kind) | SMEs | 600 | 0 | 600 | 1159812500 | 0 | 1159812500

## MHP Commulative
MHPs Detailed Assesments/Survey
Reporting Date |  |  |  |  | 21,November,2025 |  | Post Floods Economic Recovery of Green Productive Assets in Khyber Pakhtunkhwa | [9 empty] | Reported By |  |  | Sarhad Rural Support Programme (SRSP)
General Information | [5 empty] | Timelines |  |  | Design Aspects |  |  |  |  | Transmission and Distribution Details |  |  |  |  | Beneficieries Details |  |  |  | Cost Estimates |  |  |  | Approval | [5 empty] | MHP Procurement |  |  |  |  | Physical Progress Civil | [7 empty] | Physical Progress T&D | [7 empty] | Physcial & Financial Progress EME | [7 empty] | Overall Progress
S. No | District | Tehsil | VC/NC | Village | Type of MHP | Dialogue With Community | Social Assessmnent | Detailed Technical Survey | Existing Capacity (KW) | Total Capacity kW | Net Head ft | Discharge cusecs | Length of Channel ft | Turbine Type | No of Turbines required | HT Line Length (Km) | LT Line Length (Km) | No. of Transformer | Total H.H | Commercial Consumers | Total Connections | Total Population | Total Cost (PKR) | Per Kw Cost (PKR) | Per HH+Commercial Cost (PKR) | Per Beneficiery Cost (PKR) | Presented to Management Committee | Shared With OPM/EU for Review | Review Meeting with OPM (TA/EU) comments and feedback | OPM Visit to Site | Final Review Meeting with EU for Approval | Approval from EU | Advertisement in Newspaper | Pre-Bid Meeting | Technical Bid Opening | Financial Bid Opening | Contractor Agreement & Work Order | Date of T&D work Initiation Layout and Ground Breaking Ceremony | Total Amount for Civil Works PKR | Financial Progress | Amount Disbursed | Remaining | Physical Progress | Progress Description | Date of Physical Work completion | Date of T&D work Initiation | Total Amount for T&D Works PKR | Amount Disbursed T&D | Financial Progress T&D % | Remaining Amount T&D | Physical Progress T&D | Progress Description T&D | Date of Physical Work completion T&D | Date of EME work Initiation | Total Amount for EME Works PKR | Amount Disbursed EME | Financial EME Progress % | Remaining EME | Physical EME Progress | Progress EME Description | Date of Physical Work completion EME | Physical (Civil+EME+T&D) % | Description Progress Overall | Amoount Disbursed PKR Overall | Remaining Amount | Fianncial Progress %
1 | Shangla | Alpuri | Damorai | Damorai | Rehab | 2025-01-21 | 2025-01-23 | 2025-01-24 | 560 | 560 | 90 | 120 | 1900 | Francis | N/A | N/A | N/A | N/A | 1298 | 98 | 1396 | 9910.204 | 144792619 | 258558.2482 | 103719.6411 | 14610.458 | 2025-06-10 | 2025-07-23 | 2025-07-25 | 2025-06-27 | 2025-08-01 | 2025-08-11 | 2025-09-05 | 2025-09-25 | 2025-10-07 | [5 empty] | 0 | #VALUE! | 0% | [6 empty] | 0 | 0% | [6 empty] | 0 | 0% |  |  |  |  | 0 | 144792619 | 0%
2 | Upper Dir | Kalkot | Thall | Thall | Upgradation | 2025-01-03 | 2025-01-17 | 2025-01-17 | 600 | 2500 | 153 | 209 | 5666 | Francis | 2 | 20 | 34 | 20 | 4044 | 150 | 4194 | 30390.5133 | 783135306 | 313254.1224 | 186727.5408 | 25769.0713 | 2025-02-04 | 2025-02-04 | 2025-03-21 | 2025-04-17 | 2025-05-06 | 2025-05-16 | 2025-05-31 | 2025-07-11 | 2025-07-22 | 2025-07-28 |  | 2025-10-02 |  | 0% | 0 | 0 | 3% | 1. Intake structure excavation complete. 2. channel leveling for 400 ft completed. 3. Work on gabion structure is in progress. 4. Steel cutting for the intake structure is in progress. 5. Steel fixing for the channel is in progress. | [5 empty] | 0 | 0% | [6 empty] | 0 | 0% |  |  | 1% | 1-Civil Works In progress 2- T&D and EME not Initiated | 0 | 783135306 | 0%
3 | Lower Chitral | Chitral | Ayun | Ayun | Upgradation | 2025-01-10 | 2025-03-15 | 2025-02-25 | 700 | 700 | 105.78 | 90 | 2460 | Francis | N/A | 1.6667 | 2 | 6 | 692 | 28 | 720 | 5011 | 202525488 | 289322.1257 | 281285.4 | 40416.182 | [14 empty] | 0 | #VALUE! | 0% | [6 empty] | 0 | 0% | [6 empty] | 0 | 0% |  |  |  |  | 0 | 202525488 | 0%
4 | Lower Chitral | Chitral | Bamburete | Sarujalik | New | 2025-01-10 | 2025-01-10 | 2025-05-14 | 200 | 500 | 168 | 52.5 | 2400 | Francis | 1 | 9 | 9 | 10 | 650 | 130 | 780 | 5429.6832 | 303264528 | 606529.056 | 388800.6769 | 55853.0792 | [14 empty] | 0 | #VALUE! | 0% | [6 empty] | 0 | 0% | [6 empty] | 0 | 0% |  |  |  |  | 0 | 303264528 | 0%
5 | Lower Chitral | Chitral | Ayun | Ayun-2 | New | 2025-01-17 | 2025-03-15 | 2025-02-25 | 0 | 2000 | 197.4 | 173 | 5600 | Francis | 2 | 20.8 | 34.525 | 19 | 2379 | 290 | 2669 | 18416.1 | 1000586983 | 500293.4915 | 374892.088 | 54332.1867 | [14 empty] | 0 | #VALUE! | 0% | [6 empty] | 0 | 0% | [6 empty] | 0 | 0% |  |  |  |  | 0 | 1000586983 | 0%
6 | Lower Chitral | Chitral | Golain | Birmogh | Rehab | 2025-01-27 | 2025-03-10 | 2025-05-16 | 2000 | 2000 | 169 | 160 | 2100 | Francis | N/A | 4.3333 | 2 | 5 | 300 | 25 | 325 | 2242.5 | 281551536 | 140775.768 | 866312.4185 | 125552.5244 | [14 empty] | 0 | #VALUE! | 0% | [6 empty] | 0 | 0% | [6 empty] | 0 | 0% |  |  |  |  | 0 | 281551536 | 0%
7 | Swat | Bahrain | Keedam | Keedam | New | 2025-01-12 | 2025-01-28 | 2025-09-24 | 0 | 4500 | 375 | 185 | 3500 | Francis | 3 | 111.837 | 288.266 | 50 | 2084 | 423 | 2507 | 17671.843 | 1240490096.25 | 275664.4658 | 494810.5689 | 70195.8532 | [14 empty] | 0 | 0 | 0% | [6 empty] | 0 | 0% | [6 empty] | 0 | 0% |  |  |  |  | 0 | 1240490096.25 | 0%
Total | [8 empty] | 4060 | 12760 |  |  | 23626 | 0 | 8 | 55.8 | 81.525 | 110 | 11447 | 1144 | 12591 | 71400.0006 | 3956346556.25 | 2108732.8118 | 2696548.3342 | 386729.3548

## MHP Dashboard
PEACE II PROJECT
HPPs PROGRESS
Target 16.3 MW
PROCESS Progress |  |  | 2025-11-18
HPPs Priortitized |  | CBOs Formed/Dialogues |  | Detailed Designs and Cost Estimates |  | Approved by EU/OPM |  | Initiated |  | Completed
16 | Nos | 3 | Nos | 7 | Nos | 2 | Nos | 1 | Nos | 0 | Nos
16.3 | MW |  |  | 12.76 | MW | 3.06 | MW | 2.5 | MW | 0 | MW
Schemes Cost PKR
Total Cost Designed HPPs Million PKR |  |  |  | 3956346556.25 |  | Target /kW Cost | 398558 | Average /KW Cost of Designed |  | 340628.1825
10.1 M
Beneficieries
CBO Memebers |  | Beneficieries HHs+Commercial Units |  |  | Avg HH HPP |  |  | Target HHs Per KW |  | Projected HHs Per KW Designed HPPs
|  | 12591 |  |  | 1798.7143
73 | [7 empty] | 1.3598 |  | 0.98676 |  | 59 T

## MHP Detail Design Cost Estimate
MHPs Detailed Assesments/Survey
Reporting Date |  |  |  |  | 31,August,205 |  | Post Floods Economic Recovery of Green Productive Assets in Khyber Pakhtunkhwa | [10 empty] | Reported By |  |  | Sarhad Rural Support Programme (SRSP)
General Information | [5 empty] | Timelines |  |  |  | Design Aspects |  |  |  |  | Transmission and Distribution Details |  |  |  |  | Beneficieries Details |  |  |  | Cost Estimates
S. No | District | Tehsil | VC/NC | Village | Type of MHP | Dialogue With Community | Social Assessmnent | Detailed Technical Survey | Reviewed by EU /OPM | Existing Capacity (KW) | Total Capacity kW | Net Head ft | Discharge cusecs | Length of Channel ft | Turbine Type | No of Turbines required | HT Line Length (Km) | LT Line Length (Km) | No. of Transformer | Total H.H | Commercial Consumers | Total Connections | Total Population | Total Cost (PKR) | Per Kw Cost (PKR) | Per HH+Commercial Cost (PKR) | Per Beneficiery Cost (PKR)
1 | Shangla | Alpuri | Damorai | Damorai | Rehab | 2025-01-21 | 2025-01-23 | 2025-01-24 | Yes | 560 | 560 | 90 | 120 | 1900 | Francis | N/A | N/A | N/A | N/A | 1298 | 98 | 1396 | 9910.204 | 144792619 | 258558.2482 | 103719.6411 | 14610.458
2 | Upper Dir | Kalkot | Thall | Thall | Upgradation | 2025-01-03 | 2025-01-17 | 2025-01-17 | Yes | 600 | 2500 | 153 | 209 | 5666 | Francis | 2 | 20 | 34 | 20 | 4044 | 150 | 4194 | 30390.5133 | 783135306 | 313254.1224 | 186727.5408 | 25769.0713
3 | Lower Chitral | Chitral | Ayun | Ayun | Upgradation | 2025-01-10 | 2025-03-15 | 2025-02-25 |  | 700 | 700 | 105.78 | 90 | 2460 | Francis | N/A | 1.6667 | 2 | 6 | 692 | 28 | 720 | 5011 | 202525488 | 289322.1257 | 281285.4 | 40416.182
4 | Lower Chitral | Chitral | Bamburete | Sarujalik | New | 2025-01-10 | 2025-01-10 | 2025-05-14 |  | 200 | 500 | 168 | 52.5 | 2400 | Francis | 1 | 9 | 9 | 10 | 650 | 130 | 780 | 5429.6832 | 303264528 | 606529.056 | 388800.6769 | 55853.0792
5 | Lower Chitral | Chitral | Ayun | Ayun-2 | New | 2025-01-17 | 2025-03-15 | 2025-02-25 |  | 0 | 2000 | 197.4 | 173 | 5600 | Francis | 2 | 20.8 | 34.525 | 19 | 2379 | 290 | 2669 | 18416.1 | 1000586983 | 500293.4915 | 374892.088 | 54332.1867
6 | Lower Chitral | Chitral | Golain | Birmogh | Rehab | 2025-01-27 | 2025-03-10 | 2025-05-16 |  | 2000 | 2000 | 169 | 160 | 2100 | Francis | N/A | 4.3333 | 2 | 5 | 300 | 25 | 325 | 2242.5 | 281551536 | 140775.768 | 866312.4185 | 125552.5244
7 | Swat | Bahrain | Keedam | Keedam | New | 2025-01-12 | 2025-01-28 | 2025-09-24 |  | 0 | 4500 | 375 | 185 | 3500 | Francis | 3 | 111.837 | 288.266 | 50 | 2084 | 423 | 2507 | 17671.843 | 1240490096.25 | 275664.4658 | 494810.5689 | 70195.8532
Total | [9 empty] | 4060 | 12.76 |  |  | 23626 | 0 | 8 | 55.8 | 81.525 | 110 | 11447 | 1144 | 12591 | 71400.0006 | 3956346556.25 | 340628.1825 | 2696548.3342 | 386729.3548

## MHPs Approval
MHP Approval Timeline
Reporting Date: |  | 18 November,2025
MHPs Approval Timeline
S. No | District | Tehsil | VC/NC | Village | Type of MHP (New/Rehab/Upgradation) | Detail Design & Cost Estimation Prepared | Presented to Management Committee | Shared With OPM/EU for Review | Review Meeting with OPM (TA/EU) comments and feedback | OPM Visit to Site | Final Review Meeting with EU for Approval | Approved MW from EU | Approval Date
1 | Shangla | Alpuri | Damorai | Damorai | Rehab | 2025-06-12 | 2025-06-10 | 2025-07-23 | 2025-07-25 | 2025-06-27 | 2025-08-01 | 0.56 | 2025-08-11
2 | Upper Dir | Kalkot | Thall | Thall | Upgradation | 2025-01-31 | 2025-02-04 | 2025-02-04 | 2025-03-21 | 2025-04-17 | 2025-05-06 | 2.5 | 2025-05-16
3 | Lower Chitral | Chitral | Bamburete | Sarujalik | New | 2025-07-25 | 2025-10-10 | 2025-10-28
4 | Lower Chitral | Chitral | Ayun | Ayun | Rehab | 2025-07-29 | 2025-10-10 | 2025-10-28
5 | Lower Chitral | Chitral | Golain | Birmogh | Rehab | 2025-07-25 | 2025-10-10 | 2025-10-28
8 | Lower Chitral | Chitral | Ayun | Ayun-2 | New | 2025-07-20 | 2025-10-10 | 2025-10-28

## MHP Procurement
MHP Procurement (Civil Works)
Reporting Date: |  | 31 August,2025
MHPs Approval Timeline
S. No | District | Tehsil | VC/NC | Village | Type of MHP (New/Rehab/Upgradation) | Advertisement in Newspaper | Pre-Bid Meeting | Technical Bid Opening | Financial Bid Opening | Contractor Agreement & Work Order
1 | Shangla | Alpuri | Damorai | Damorai | Rehab | 2025-09-05 | 2025-09-25 | 2025-10-07
2 | Upper Dir | Kalkot | Thall | Thall | Upgradation | 2025-05-31 | 2025-07-11 | 2025-07-22 | 2025-07-28
3 | Lower Chitral | Chitral | Bamburete | Sarujalik | New
4 | Lower Chitral | Chitral | Ayun | Ayun | Upgradation
5 | Lower Chitral | Chitral | Golain | Birmogh | Rehab
6 | Lower Chitral | Chitral | Ayun | Ayun-2 | New

## Physical Progress-civil
MHP (Physical Progress-Civil Work)
Reporting Date: |  | 31 August,205
MHPs Approval Timeline
S. No | District | Tehsil | VC/NC | Village | Type of MHP (New/Rehab/Upgradation) | Capacity MW | Date of T&D work Initiation Layout and Ground Breaking Ceremony | Total Amount for Civil Works PKR | Financial Progress | Amount Disbursed | Remaining | Physical Progress | Progress Description | Date of Physical Work completion
1 | Upper Dir | Kalkot | Thall | Thall | Upgradation | 2.5 | 2025-10-02 |  | 0% | 0 | 0 | 3% | 1. Intake structure excavation complete. 2. channel leveling for 400 ft completed. 3. Work on gabion structure is in progress. 4. Steel cutting for the intake structure is in progress. 5. Steel fixing for the channel is in progress.

## Irrigation Dashboard
PEACE II PROJECT
IRRIGATION SCHEMES PROGRESS
Target |  | 100 Community Based Schemes
PROCESS Progress
CBOs Formation | Schemes Surveyed |  | Detail Design Finalized | Schemes Initiated |  | Schemes Completed | O&M Trainings | Schemes HandedOver
12 | 12 |  | 12 | 0 |  | 0 | 0 | 0
Schemes Cost PKR
Total Schemes Cost PKR |  |  | 58813400 |  |  |  | Average Scheme Cost | 4901116.6667
10.1 M
Beneficieries
CBO Memebers | Beneficieries HHs |  |  |  | Avg HH /Scheme |  | Target HHs 100 Schemes | Per HH Cost
247 | 2048 |  |  |  | 170.6667 |  | 17000 | 28717.4805 | 59 T
Command Area Coverage
Total Command Area (Kanal) | Length of Irrigation Channel (Km) |  | Additional Area covered
11649.8 | 41.8665 |  | 2312.3
1
1

## Irrigation Scheme Detail
Irrigation Detailed Assesments/Survey
Reporting Date | [7 empty] | 31,August,205 |  |  | Post Floods Economic Recovery of Green Productive Assets in Khyber Pakhtunkhwa | [14 empty] | Reported By | Sarhad Rural Support Programm
General Information | [8 empty] | Timelines | [8 empty] | Beneficiaries and Command Area |  |  |  |  | Design Aspects |  |  |  |  | Project Cost |  | Progress
S. No | District | Tehsil | VC/NC | Village | CBO Name | CBO Members | Type of Scheme | Duration of the Project | Dialogue With Community | CBO Formation Date | Social Assessmnent | Detailed Technical Survey | Detail Design Finalized | Initiated | Completed | O&M trainings | Handed Over | Beneificiery HHs | Beneficiary (Farmers) | Total Command Area (Kanal) | Length of Irrigation Channel (Km) | Additional Area covered before/ after rehabilitation | Channel Running Feet REHAB | Channel Running Feet NEW | Total Channel Running Feet | Protection Running Feet | Intake Length Running Feet | Per Household cost | Scheme Cost | Physcical Progress % | Financial Progress %
1 | Swat | Behrain/Swat | Mankiyal | Mankiyal | Zarai Taraqiati Committee Mankyal | 20 | Rehab | 8 Months | 2025-01-02 | 2025-06-12 | 2025-01-08 | 2025-05-29 | 2025-06-04 |  |  |  |  | 250 | 106 | 1428 | 11 | 550 | 12800 | 460 | 13260 | 222 | 120 | 71528.3019 | 7582000
2 | Upper Chitral | Mulkhow | Morder Muzgole | Morder | Zoom Community Organization Morder | 25 | Rehab | 8 Months | 2025-01-10 | 2025-06-12 | 2025-01-22 | 2025-07-17 | 2025-07-22 |  |  |  |  | 200 | 200 | 1874 | 1.51 | 655.9 | 1200 | 800 | 2000 | 180 | 0 | 15200 | 3040000
3 | Upper Dir | Kalkot | Thall | Thall Landi | CBO Landai Thall | 20 | Rehab | 8 Months | 2025-01-03 | 2025-06-24 | 2025-01-17 | 2025-05-26 | 2025-07-30 |  |  |  |  | 180 | 42 | 816 | 5.9997 | 163.2 | 3315 | 0 | 19685 | 435 | 50 | 174642.8571 | 7335000
4 | Upper Dir | Kalkot | Thall | Thall Kalan Bala Payeen | CBO Zarai Taraqiati Tanzeem Thall | 17 | Rehab | 8 Months | 2025-01-03 | 2025-07-22 | 2025-01-17 | 2025-05-27 | 2025-07-30 |  |  |  |  | 180 | 55 | 1336 | 1.7068 | 267.2 | 950 | 0 | 5600 | 420 | 50 | 153903.6364 | 8464700
5 | Upper Dir | Kalkot | Thall | Thall Bazar | CBO Zarai Taraqiati Tanzeem Thall Bazar | 17 | Rehab | 8 Months | 2025-01-03 | 2025-07-22 | 2025-01-17 | 2025-05-27 | 2025-07-30 |  |  |  |  | 160 | 36 | 677 | 1.5 | 135.4 | 2610 | 0 | 4921.5 | 120 | 50 | 172797.2222 | 6220700
6 | Shangla | Alpuri | Damorhai | Kikor | CBO Kashtkaar Tanzeem Kikor | 20 | Rehab | 8 Months | 2023-01-21 | 2025-06-27 | 2023-01-23 | 2025-06-27 | 2025-03-07 |  |  |  |  | 39 | 39 | 503 | 1.25 | 100.6 | 195 | 695 | 890 | 0 | 60 | 48974.359 | 1910000
7 | Shangla | Alpuri | Karshat | Karshat | MCO Karshat Zameendar | 20 | Rehab | 8 Months | 2025-01-16 | 2025-07-17 | 2025-02-11 | 2025-06-29 | 2025-03-07 |  |  |  |  | 22 | 22 | 400 | 1.25 | 80 | 155 | 2500 | 2655 | 0 | 45 | 106000 | 2332000
8 | Lower Chitral | Chitral | Koghuzi | Birmogh Golain | CBO Birmogh Golain | 20 | Rehab | 8 Months | 2025-01-27 | 2025-09-18 | 2025-03-10 | 2025-09-13 | 22 Sept, 2025 |  |  |  |  | 60 | 20 | 105.3 | 3.1 | 0 | 500 | 0 | 500 | 140 | 0 | 200000 | 4000000
9 | Lower Chitral | Chitral | Bamburete | Sarujalik | CBO Sarujalik-Gambayak | 21 | Rehab | 8 Months | 2025-01-10 | 2025-09-10 | 2025-01-10 | 2025-09-09 | 22 Sept, 2025 |  |  |  |  | 50 | 21 | 253.5 | 4.56 | 0 | 900 | 0 | 900 | 200 | 0 | 184142.8571 | 3867000
10 | Lower Chitral | Chitral | Ayun-1 | Balawosht Payeen | CBO Balawosht Payeen | 20 | Rehab | 8 Months | 2025-01-10 | 2025-09-11 | 2025-03-15 | 2025-10-09 | 22 Sept, 2025 |  |  |  |  | 120 | 20 | 780 | 5.5 | 0 | 1532 | 0 | 1532 | 200 | 150 | 348900 | 6978000
11 | Lower Chitral | Chitral | Ayun-2 | Sahan | CBO sahan | 27 | Rehab | 8 Months | 2025-01-17 | 2025-09-18 | 2025-03-15 | 2025-09-17 | 22 Sept, 2025 |  |  |  |  | 400 | 27 | 1677 | 3.1 | 0 | 550 | 0 | 550 | 0 | 170 | 122259.2593 | 3301000
12 | Lower Chitral | Chitral | Ayun-1 | Derkhanandeh | CBO Darkhnanda | 20 | Rehab | 8 Months | 2025-01-18 | 2025-10-17 | 2025-03-15 | 2025-09-29 | 2025-10-23 |  |  |  |  | 387 | 24 | 1800 | 1.39 | 360 | 300 | 0 | 300 | 80 | 200 | 157625 | 3783000
Total | [5 empty] | 247 | 12 |  |  | 12 | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 2048 | 612 | 11649.8 | 41.8665 | 2312.3 | 25007 | 4455 | 52793.5 | 1997 | 895 |  | 58813400